## AndroidApp
Version | Date | Problem | Solution | Procedure Impact | Table Impact | Process Involve | Delivered To Client(Yes/No) | Client Delivery Date
Ver 5.0 | 2019-08-01 | New Version Check | New Button To download app |  |  | Login Screen | Yes | 2019-08-21
Ver 6.0 | 2019-08-26 | Final Packinging Make Trolley pack size editable | Pass packsize of trolley everytime and if last one and new one is change then update packsize in trolley master |  |  | FinalPacking | Yes | 2019-08-27
Ver 6.5 | 2019-08-30 | New Screnn To Add New Trolley And Print |  |  |  |  | YES | 2019-09-11
Ver 6.6 | 2019-09-18 | On Machining Screen Give Input Option for operator & inspector |  |  |  | Machining | Yes | 2019-09-23
Ver 6.7 | 2019-10-04 | DispatchOrderNo For Dispatch |  |  |  |  | yes | 2019-10-09
Ver 7.0 | 2019-10-14 | Machining Model Split Option |  |  |  |  | yes | 2019-11-05
Ver 7.1 | 2019-11-27 | On Machining Split User Should create new model while cutting trolley is mixed |  |  |  | Machining Split | Yes | 2019-11-27
Ver 7.1 | 2019-12-05 | Model No HSPP-Z4M/Z4V shold not show on Machining Split |  |  |  |  | yes | 2019-12-05

## CommServer
Version | Date | Problem | Solution | Procedure Impact | Table Impact | Process Involve | Delivered To Client(Yes/No) | Client Delivery Date
4.0.0.0 | 2019-08-01 | Check New version at the time login for both android and desktop app | In Bin folder there will be one folder NewApp which will two folder AndroidApp,DesktopApp these two folder will have updated latest exe/apk then comm server will return latest bytes whenever it will be called | Just Add New Folder manually in Commserver |  | Login Screen | YES | 2019-08-21
5.0.0.0 | 2019-08-27 | Final Packinging Make Trolley pack size editable | Pass packsize of trolley everytime and if last one and new one is change then update packsize in trolley master |  |  | Finalpacking | Yes | 2019-08-27
6.0.0.0 | 2019-08-30 | New Screnn To Add New Trolley And Print | Add New Prn For BoxTrolley |  |  |  | YES | 2019-09-11
6.0.0.5 | 2019-09-18 | On Machining Screen Give Input Option for operator & inspector |  |  |  |  | Yes | 2019-09-23
6.0.0.7 | 2019-10-04 | DispatchOrderNo For Dispatch |  |  |  |  | yes | 2019-10-09
7.0.0.0 | 2019-10-14 | Machining Model Split Option |  |  |  |  | YES | 2019-11-05
7.0.0.1 | 2019-10-14 | On Machining Split User Should create new model while cutting trolley is mixed |  |  |  |  | yes | 2019-11-27
7.0.0.2 | 2019-12-05 | During Maching Process Trolley card Scan HSPP-Z4M/Z4V model no should not be allowed |  |  |  |  | yes | 2019-12-05

## DesktopApp
Version | Date | Problem | Solution | Procedure Impact | Table Impact | Process Involve | Delivered To Client(Yes/No) | Client Delivery Date
4.0.0.0 | 2019-08-01 | Check New version at the time login | If new version found then download it from comm server using new exe from console app | Add Three lines in dbSetting file for Comm server IP, Port And Exe name |  | Login Screen | YES | 2019-08-21
| 2019-08-19 | Machining report should show line no | Change in comm server and in app | Prc_Rpt_Machining |  | Machining Report | YES | 2019-08-21
| 2019-08-19 | Show Current Shift Trolley Count As Per Process | Create New Procedure And Add DashBoard.Add New TimerValue To table For TrolleyCount | [Prc_GetCurrentShiftTrolleyCount] | TimerTimeSetting | Main Menu,Login | YES | 2019-08-21
5.0.0.0 | 2019-08-21 | FinalPacking Report Show Dispatch Recod as Green | Now Procedure will return status to change the color | Prc_Rpt_FinalPacking |  | Final Packing Report | YES | 2019-08-22
| 2019-08-21 | Show Dispatch Trolley Count |  | [Prc_GetCurrentShiftTrolleyCount] |  | Main Menu DashBoard | YES | 2019-08-22
| 2019-08-21 | Dispatch Order Reversal Option | New Form | [Prc_Dispatch_Cancel] |  |  | YES | 2019-08-22
| 2019-08-22 | Excel Export Option in reports |  |  |  | All Reports | YES | 2019-08-22
| 2019-08-22 | Trolley Receiving History Report | Add New value To Module Master "Trolley Receiving History" | [Prc_Rpt_TrolleyReceiving] |  |  | YES | 2019-08-22
5.0.0.2 | 2019-08-27 | Show Incomplete Trolely In Finalpacking report as red |  |  |  |  | YES | 2019-08-27
5.0.0.3 | 2019-08-28 | Dispatch Report hightlight trolley which are not received yet |  |  |  |  | Yes | 2019-08-28
5.0.0.4 | 2019-08-29 | Show trolleycount pending for receiving on dashbarod |  |  |  |  | YES | 2019-08-29
6.0.0.0 | 2019-09-09 | After Machining Hold/Unhold screen |  |  |  |  | YES | 2019-09-11
6.0.0.1 | 2019-09-18 | Show operator and inspector name in machining and final packing report |  |  |  |  | Yes | 2019-09-23
| 2019-09-22 | In Dispatch order allow use to edit order after complete | Give filter option to search old dispatch order |  |  |  | yes | 2019-09-23
6.0.0.5 | 2019-09-25 | Change dashboard |  |  |  |  | yes | 2019-09-26
6.0.0.7 | 2019-09-27 | Add Comment For Update in Production Order |  |  |  |  | YES
| 2019-09-27 | In model master map the every model to maximum qty so that during cutting process user can not input ok qty more than model maximum qty. |  |  |  |  | yES | 2019-10-09
| 2019-09-27 | In trolley master user can select 2 trolley no and print 2 trolley barcode on same label. | Update TROLLEY.PRN |  |  |  | Yes | 2019-10-09
| 2019-09-30 | Partial NG After Machining |  |  |  |  | yES | 2019-10-09
| 2019-10-04 | DispatchOrderNo For Dispatch |  |  |  |  | yES | 2019-10-09
7.0.0.0 | 2019-10-09 | Auto Generate charge no and pallet no in cutting |  |  |  |  | YES | 2019-10-11
7.0.0.3 | 2019-12-05 | Pikcing Report |  |  |  |  | yes | 2019-12-05
8.0.0.0 | 2020-01-06 | Add Option For another Line |  |  |  |  | yES | 2020-01-16
8.0.0.1 | 2020-01-29 | Show Line No In Cutting Report |  |  |  |  | YES | 2020-02-03
9.0.0.0 | 2020-03-02 | Add line no in production p lan and show data on cutting based on line wise production plan |  |  |  |  | YES | 2020-03-02
9.0.0.1 | 2020-03-13 | Show Line No in QA report and Machining report &QA color code |  |  |  |  | yes
9.0.0.2 | 2020-06-15 | Add Maching date in final packing report |  |  |  |  | YES | 2020-06-15
10.0.0.1 | 2020-08-20 | Customer Return Option |  |  |  |  | YES | 2020-09-29
| 2020-09-22 | Trolle card delete |  |  |  |  | YES | 2020-09-29

## DataBase
Version | Date | Problem | Solution | Procedure Impact | Table Impact | Process Involve | Delivered To Client(Yes/No) | Client Delivery Date
| 2019-08-01 | Check New Version | Create New Table And Procedure | Prc_GetAppVersion | AppVersion | Desktop App And Android App at the time of login wil check new version | YES | 2019-08-21
| 2019-08-21 | Change color in Final Packing Report based on status |  | Prc_Rpt_FinalPacking |  | Final Packing Report | YES | 2019-08-22
| 2019-08-21 | Show Disptch Trolley Count On dashboard |  | [Prc_GetCurrentShiftTrolleyCount] |  | Main Menu dashboard | YES | 2019-08-22
| 2019-08-21 | Dispatch Order Reversal Option | New Table DispatchDetail_Deleted,Add Dispatch Delete Value To Module Master | [Prc_Dispatch_Cancel] | DispatchDetail_Deleted,Module Master |  | YES | 2019-08-22
| 2019-08-22 | Link Trolley Receiving To Dispatch Order | Add new Column in TrolleyReceiving Table DispatachOrderId And Make Id column as Primary Key | PRC_TROLLEY_REC | TrolleyReceiving |  | YES | 2019-08-22
| 2019-08-22 | Trolley Receiving History Report | Add New value To Module Master "Trolley Receiving History" | [Prc_Rpt_TrolleyReceiving] | ModuleMaster |  | YES | 2019-08-22
| 2019-08-26 | FinkaPacking packsize editable |  | [Prc_Get_FinalPacking_Data] |  |  | Yes | 2019-08-27
| 2019-08-27 | FinkaPacking packsize editable | Update Procedure to update the trolley master packsize. Add 2 New Column In TrolleyMaster - @ModifyOn,@ModifyBy | [Prc_SaveFinalPackingData] | TrolleyMaster |  | YES | 2019-08-27
| 2019-08-27 | Show Incomplete Trolely In Finalpacking report as red |  | [Prc_Rpt_FinalPacking] |  |  | yes | 2019-08-27
| 2019-08-28 | Dispatch Report hightlight trolley which are not received yet |  | [Prc_Rpt_Dispatch] |  |  | Yes | 2019-08-28
| 2019-08-29 | Show trolleycount pending for receiving on dashbarod |  | [Prc_GetCurrentShiftTrolleyCount] |  |  | YES | 2019-08-29
| 2019-08-30 | Add/Print trolley in HHT | Add New Column in TrolleyMaster ModelNo | [Prc_TrolleyMaster_FromHHT] |  |  | YES | 2019-09-11
| 2019-09-04 | Because of above problem |  | [Prc_Rpt_FinalPacking] |  |  | YES | 2019-09-11
| 2019-09-09 | Add modify on modify by in trolley master |  | [Prc_TrolleyMaster] |  |  | YES | 2019-09-11
| 2019-09-09 | After Machining Hold/Unhold | Add New Module In Module Master For Hold Unhold 215,Add New column machining IsHold,HoldOn,HOldBy | [Prc_MachiningHold],[Prc_Get_FinalPacking_Data] | Machining |  | YES | 2019-09-11
| 2019-09-11 | Show dispatach order id in dispatch report |  | [Prc_Rpt_Dispatch] |  |  | YES | 2019-09-11
| 2019-09-18 | Add Inspector and Operator on Machining | Add 2 Column in machining Operator,Inspector | [Prc_SaveMachiningData] | Machining |  | Yes | 2019-09-23
| 2019-09-18 | Speeling Mistake in message |  | [Prc_Get_FinalPacking_Data] |  |  | Yes | 2019-09-23
| 2019-09-18 | Show Inspection operator in Machining and final packing reprot |  | [Prc_Rpt_Machining],[Prc_Rpt_FinalPacking] |  |  | Yes | 2019-09-23
| 2019-09-22 | In Dispatch order allow use to edit order after complete |  | [Prc_DispatchOrder],[Prc_Rpt_Machining] |  |  | YEs | 2019-09-23
| 2019-09-25 | Change dashboard | Add New Table NgPercentageValue and add value to it/Add New Entry In Module master For NG% | [Prc_GetDashBoardData],[Prc_NGPercentage] | NgPercentageValue,Module Master |  | YES
| 2019-09-25 | Show Trolley Is returnable or not in trolley master | Add New Column In TrolleyMaster For IsReturnable bit | Prc_TrolleyMaster | TrolleyMaster |  | YES
| 2019-09-26 | Show Time in dispatch report |  | [Prc_Rpt_Dispatch],[Prc_Rpt_TrolleyReceiving] |  |  | YES
| 2019-09-26 | Tray Qty And Color update in trolley receiving |  | [PRC_ColorMaster],[PRC_TROLLEY_REC] |  |  | YES
| 2019-09-27 | Add Comment For Update in Production Order | Add New Colum to ProductionPlan Table Remarks & Create New Table ProductionPlan_ChangeHistory | Prc_ProductionPlan | ProductionPlan,ProductionPlan_ChangeHistory |  | Yes
| 2019-09-27 | In model master map the every model to maximum qty so that during cutting process user can not input ok qty more than model maximum qty. | Add New Column To Model Master CuttingMaxQty,ModifyOn,ModifyBy | [Prc_ModelMaster] | ModelMaster |  | yes
| 2019-09-27 | Partial NG After Cutting | Add New Column Cutting QAHoldOn,QAPartialNgQtyQAPartialNgReason | [Prc_QA],[Prc_Get_Machining_Data],[Prc_GetDashBoardData],[Prc_GetRePrintData],[Prc_Picking_For_Machining_Data],[Prc_QASample] | Cutting | QA | YES | 2019-10-09
| 2019-09-30 | Partial NG After Machining | Add New Value In Module Master After Machining NG,Add 3 Column In Machining Table QANgQty,QAOn,QABY | [Prc_QA_Machining],[Prc_Get_FinalPacking_Data],[Prc_Get_ReOiling_Data],[Prc_GetDashBoardData],[Prc_GetRePrintData],[Prc_Dispatch_Cancel] | Machining,ModuleMaster |  | YES | 2019-10-09
| 2019-09-30 | DispatchOrderNo For Dispatch | Remove Old PrimaryKey From DispatchOrder Table,Add New Column DispatchOrderNo,SrNo,Make DispatchOrderNo Primary Key | [Prc_DispatchOrder],[Prc_GetDispatchData] |  |  | YES | 2019-10-09
| 2019-10-09 | Auto Generate charge no and pallet no in cutting | Add 2 Column in Cutting, - ChageNo,PalletNo, Add New Value In Module Master Cutting Manual ChargeNo | [Prc_GetChargePalletNo],[Prc_SaveCuttingData],[Prc_Update_Cutting_Trolley] | Cutting,ModuleMaster |  | yES | 2019-10-10
| 2019-10-14 | Machining Model Split Option |  | [Prc_Get_Machining_Split_Data],[Prc_SaveMachiningSplitData] |  |  | YES | 2019-11-05
| 2019-11-27 | On Machining Split User Should create new model while cutting trolley is mixed |  | [Prc_Get_Machining_Split_Data],[Prc_SaveMachiningSplitData] |  |  | YEs | 2019-11-27
| 2019-12-05 | During Maching Process Trolley card Scan HSPP-Z4M/Z4V model no should not be allowed | Add Value To Module Master 309 Picking Report True | Prc_Get_Machining_Data,[Prc_GetModel_ForMachiningSplit],[Prc_Rpt_Picking] |  |  | YES | 2019-12-05
| 2020-01-06 | Add New Line For Cutting | Add New Column To Cutting Table Line_No | Prc_GetChargePalletNo,Prc_SaveCuttingData |  |  | yES | 2020-01-16
| 2020-01-29 | Show Line No In Cutting Report |  | [Prc_Rpt_Cutting] |  |  | Yes | 2020-02-03
| 2020-03-02 | Add line no in production p lan and show data on cutting based on line wise production plan | Add New Column As LineNo in productionPlan table | [Prc_ProductionPlan],[Prc_GetCuttingData] |  |  | YES | 2020-03-02
| 2020-03-13 | Show Line No in QA report and Machining report &QA color code |  | Prc_Rpt_QA,Prc_Rpt_Machining |  |  | YES
| 2020-06-15 | Add machining date on Final packing report |  | [Prc_Rpt_FinalPacking] |  |  | YES | 2020-06-15
| 2020-08-20 | Customer Return Optioin | Add 2 new column PartialClose and reason | [Prc_CustomerReturn] | DispatchOrder |  | YES
| 2020-09-22 | Delete trolley card | add in module master | [Prc_Delete_TrolleyCard] | Create new table Delete_History |  | YES | 2020-09-29
|  | Update Cutting Trolley Card | Give option to change model | Prc_Update_Cutting_Trolley |  |  | YES | 2020-09-29
|  | Add Machining table value of cutting lineno |  | [Prc_SaveMachiningData,[Prc_SaveMachiningSplitData |  |  | YES | 2020-09-29