## Project Schedule
Date: 22-02-19 |  |  | PROJECT SCHEDULE & TRACKER | [170 empty] | ONE YEAR WARRANTY
|  |  | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August 19 …….. | [9 empty] | Jul 20 ….
Sr# | Activity / Resource |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 2020-07-14
1 | Project Kick Off Meeting / Project Scheduling | Plan | March 4: MAHA SHIVRATRI HOLIDAY; March 21: HOLI HOLIDAY; April 19: GOOD FRIDAY HOLIDAY; May 1: LABOUR DAY HOLIDAY; June 5: RAMZAN HOLIDAY
Actual | bar: February 18 to February 22
2 | Requirement Study & BBP Sign Off | Plan | bar: February 25 to March 1; March 5 to March 8; March 11 to March 15
Actual
3 | Software Development & Unit Testing PH-I (Cutting / QA/CNC) | Plan | bar: March 18 to March 20; March 22; March 25 to March 29; April 1 to April 5; April 8 to April 12; April 15 to April 18; April 22 to April 26; April 29 to April 30; May 2 to May 3
Actual
4 | Testing at Site & UAT PH-I | Plan | bar: May 6 to May 10; May 13 to May 17
Actual
5 | Go-Live PH-I | Plan | bar: May 20 to May 24
Actual
6 | Post Go-Live Support | Plan | bar: May 27 to May 31
Actual
7 | Development & Unit Testing PH-II(Dispatch/ Empty Trolley Receiving)) | Plan | bar: May 27 to May 31; June 3 to June 4; June 6 to June 7; June 10 to June 14; June 17 to June 21; June 24 to June 28
Actual
8 | Testing at Site & UAT PH-I | Plan | bar: July 1 to July 5; July 8 to July 12
Actual
9 | Go-Live PH-I | Plan | bar: July 15 to July 19
Actual
10 | Post Go-Live Support | Plan | bar: July 22 to July 26; July 29 to August 19 …….. 2; August 19 …….. 5 to August 19 …….. 9
Actual